## Sheet1
General principles
Public functions for 2d/3d should be same if arguments exactly the same but not otherwise (rather than using same function with dummary argument, even if that happens behind the scenes)
Public functions should be fully documented in header comments
Make sure all examples only use public functions
Put all non-essential functions into code\internal if not required for general use
Function (current name) | New name | Status | 2D/3D/Both | Correct location | Action
fn_2d_add_absorbing_layer.m |  | Generalise | 2D | code | Generalise to 3D as well. Need separate 2d and 3d user functions for this one as input params different
fn_2d_add_inclusion_or_void |  | Generalise | 2D | code | Generalise to 3D as well, based on facet surface
fn_ABAQUS.m |  | Placeholder |  | code/code/internal/abaqus | Finish it! But in general, should be in code/internal functions.
fn_2d_create_smooth_random_blob.m |  | Generalise | 2D | code | Generalise to 3D as well - some sort of spherical harmonics to get random surface or is tcode easier way?
fn_2d_structured_mesh_rectangular_els.m |  | Done | 2D | code
fn_2d_structured_mesh_triangular_els.m |  | Done | 2D | code | None
fn_3d_add_absorbing_layer.m |  | Needed | 3D | code
fn_BristolFE_v2.m |  | Done | Both | code/internal
fn_calc_element_centres.m |  | Done | Both | code/internal
fn_convert_disps_to_forces_v2.m |  | Done | Both | code/internal | Should work in 3D - needs checking
fn_3d_add_inclusion_or_void |  | Needed | 3D | code
fn_display_result_v2.m |  | Done | Both | code/internal | 3D probably needs some tweaking, but basically works
fn_dist_point_to_bdry_2D.m |  | Obsolete |  | Remove | Superceded by fn_signed_dist_to_bdry.m. Check for usage in code, but eventually delete
fn_3d_find_nodes_nearest_to_surface.m |  | Needed | 3D | code | 3d version of find nodes on line in 2d. Should also return surface normals and handle multiple facets Rename both to 'nearest_to' rather than 'on'. Use fn_signed_dist_to_bdry
fn_elements_in_region2.m |  | Obsolete |  | Remove
fn_3d_structured_mesh_hexahedral_els.m |  | Done | 3D | code | Should make it so that general 3d bdry can be specified rather than just a cuboid (to provide same functionality as 2d versions)
fn_3d_tetrahedral_structured_mesh.m | fn_3d_structured_mesh_tetrahedral_els.m | Needed | 3D | code | They won't be regular tetrahedra! Should make it so that general 3d bdry can be specified rather than just a cuboid (to provide same functionality as 2d versions)
fn_find_adjacent_els.m |  |  |  | code/internal
fn_find_free_edges.m |  |  | 2D | code/internal | Need generalising for 3D - used in subdomain stuff
fn_find_free_edge_nds.m |  |  | 2D | code/internal | Need generalising for 3D - used in subdomain stuff
fn_2d_add_crack.m |  | Done | 2D | code | Needs checking (e.g. with fluid-solid interfaces but believed to work).
fn_3d_add_crack.m |  | Done | 3D | code | Needs checking (e.g. with fluid-solid interfaces but believed to work).
fn_add_fluid_solid_interface_els.m |  | Generalise | 2D | code | Generalise to 3D as well
fn_find_surrounding_els.m |  |  |  | code/internal
fn_find_surrounding_nds.m |  |  |  | code/internal
fn_elements_in_region.m |  | Update |  | code | Check why 2 functions - poss one uses mod and the other uses nds and els. probably need new version for 2D and 3D that uses fn_signed_dist_to_bdry.m
fn_get_edges.m |  |  |  |  | Moved into fn_display_result
fn_estimate_max_min_vels.m |  | Done | Both | code
fn_get_plot_vals_v3.m |  | Obsolete? |  |  | Obs
fn_get_plot_vals_v4.m |  |  |  |  | Obs
fn_FE_entry_point.m |  | Done | Both | code | Tidy up. Remove options to call obsolete versions
fn_find_node_nearest_to_point.m |  | Done | Both | code | None
fn_gl_ind_for_nd_and_dof.m |  | Done |  | code/internal
fn_find_nodes_nearest_to_line.m |  | Generalise | 2D | code | Should handle multiple line segments and return surface normals at each node too. Not sure when needed, but this should be generalised in 3d too with same arguments - it doesn't need to be limited to 2d
fn_plot_3d_element.m |  |  |  |  | Obs
fn_plot_line.m |  |  |  | code/internal
fn_pogoFE.m |  | Done |  | code/internal/pogo | Need to try and get field output working
fn_point_in_element.m |  |  |  |  | Obs
fn_gaussian_pulse.m |  | Done | Both | code | None
fn_read_pogo_global_matrix_values_from_files.m |  | Done |  | code/internal/pogo
fn_get_min_max_element_sizes.m |  | Done | Both | code | None
fn_get_suitable_el_size.m |  | Done | Both | code | None
fn_get_suitable_time_step.m |  | Done | Both | code | None
fn_isotropic_stiffness_matrix.m |  | Done | Both | code | None
fn_prepare_animation.m |  | Generalise | 2D | code | Generalise to 3D as well - need to decide what 3D animation looks like!
fn_remove_fluid_solid_interface_els.m |  | Generalise | 2D | code | Generalise to 3D as well
fn_run_animation.m |  | Generalise | 2D | code | Generalise to 3D as well
fn_show_geometry.m |  | Done | Both | code | Entry point for fn_display_result_v2, but just set to show model.
fn_signed_dist_to_bdry.m |  | Done | Both | code